## Docs Gap Tracker
ID | Category | Surface | Gap/Issue | Priority | Status | Doc File | Notes
G001 | Version | Site-wide | Docs still framed as v0.0.1; v0.0.2 shipped (packs, connect, self-update) | High | Done | index.md, getting-started.md, multiple | Update version callouts
G002 | Contradiction | Gmail | quickstart/gmail.md says connect UX ships v0.0.2; connecting-services.md documents working flow | High | Done | quickstart/gmail.md | Redirect or update
G003 | Missing Guide | GPU | No public GPU drivers guide | High | Done | guides/gpu-drivers.md | Draft ready in core research
G004 | Missing Guide | Inference | No on-appliance inference guide (only external Ollama) | High | Done | guides/on-appliance-inference.md | Settings → Inference page undocumented
G005 | Missing Guide | Packs | No operator guide for /packs dashboard + kruxos pack CLI | High | Done | guides/managing-packs.md
G006 | Missing Guide | SSH | Built-in SSH opt-in (Settings → System) not documented | High | Done | guides/ssh-access.md
G007 | Incomplete | Remote Access | remote-access.md covers manual Tailscale; not built-in dashboard flow | High | Done | guides/remote-access.md | Add Settings → System section
G008 | Incomplete | Dashboard | dashboard.md missing Packs, Settings sub-pages (Hardware, Updates, License, System) | Medium | Done | quickstart/dashboard.md
G009 | Nav | Pack Authors | pack-authors/*.md orphan — not in mkdocs nav | Medium | Done | mkdocs.yml | 2 pages
G010 | Nav | Concepts | concepts/index.md not in nav | Low | Done | mkdocs.yml
G011 | Accuracy | Capabilities | Public docs say 89; codebase has 91 built-in | Medium | Done | developers/capabilities/index.md
G012 | Missing Guide | Admin CLI | admin-cli (user-token, mount, cli-config) not public | Medium | Done | guides/admin-cli.md | Exists in core repo
G013 | Missing Guide | Identities | User tokens + user policy need standalone how-to | Medium | Done | guides/user-identities.md | Partial in dashboard.md
G014 | Missing Guide | Config | No user-facing config reference | Medium | Done | guides/configuration.md | Internal config-reference.md exists
G015 | Accuracy | Updating | Says health rollback lands v0.0.2; shipped | Medium | Done | guides/updating.md
G016 | Accuracy | CLI | pack subcommand still says v0.0.1 local-only | Medium | Done | quickstart/cli.md
G017 | Accuracy | Pack Dev | developers/packs/quickstart.md v0.0.1 warnings outdated | Medium | Done | developers/packs/*.md
G018 | Missing | Code pack | kruxos-code pack (code.edit, code.multi_edit) not in capability ref | Medium | Deferred | developers/capabilities/ | Unreleased pack
G019 | Nav | Release Notes | docs/release-notes/ not linked in mkdocs | Low | Done | mkdocs.yml
G020 | Accuracy | Docker | Code Sessions Docker limitation may be fixed in v0.0.2 | Low | Done | getting-started.md, quickstart/dashboard.md | Verify against CHANGELOG
G021 | Missing Guide | Integrations | No consolidated integrations how-to (Claude+Codex+loopback) | Medium | Done | guides/host-cli-integrations.md | Core has installing-*.md drafts
G022 | Missing Guide | Code Sessions | No dedicated /code page how-to | Medium | Done | guides/code-sessions.md
G023 | Missing Guide | First Boot | Wizard steps spread across getting-started; no dedicated guide | Low | Done | guides/first-boot-wizard.md
G024 | Accuracy | Supervision port | CLI status still shows port 7701; retired per SEC-2b | Medium | Done | quickstart/cli.md
G025 | Missing | Model Registry | docs.kruxos.com/models/ not documented | Low | Deferred | guides/model-providers.md